## Timelines
id | name | group | color | goal | description | link | show | order
home | Home |  | orange | Living room painted and guest room ready before Giulia arrives on 6 November | First visit in three years; I want the flat to feel like mine |  | yes | 1
money | Money |  | green | Stop paying for things I don't use, and get the paperwork done | Feels like money leaks every month |  | yes | 2
health | Health |  | pink | Keep the routines that make me feel good |  |  | yes | 3

## Steps
timeline | track | title | kind | start | end | date | status | progress | owner | phase | pin | notes | link | show | id | importance | urgency | repeat
home |  | Get two quotes from painters | task |  |  | 2026-10-05 | done |  | me |  |  | Marco was cheaper and can come sooner |  | yes | s1 | high | high
home |  | Choose the colour for the living room | task |  |  | 2026-10-16 | todo |  | me |  |  | Between warm white and the pale green sample. Marco needs it a week before he starts. |  | yes | s2 | high | high
home |  | Marco confirms the painting dates | task |  |  | 2026-10-14 | waiting |  | Marco |  |  | He said probably 26 to 28 October. Call him on Wednesday if he hasn't confirmed. |  | yes | s3 | high | high
home |  | Living room painted | period | 2026-10-26 | 2026-10-28 |  | todo |  | Marco |  |  | Move the bookshelf the weekend before |  | yes | s4 | high | low
home |  | Clear out and clean the guest room | task |  |  | 2026-11-04 | todo |  | me |  |  | Could ask Luca to carry the boxes to the cellar |  | yes | s5 | low | high
home |  | Giulia arrives | task |  |  | 2026-11-06 | todo |  | me |  |  | Staying until 10 November |  | yes | s6 | high | low
money |  | Review subscriptions and cancel what I don't use | task |  |  | 2026-10-25 | todo |  | me |  |  | See the Subscriptions list. The gym renews on 1 November. |  | yes | s7 | high | high
money |  | Sign the will | task |  |  |  | todo |  | me |  |  | The lawyer sent the final draft; it needs an appointment to sign it in her office. No deadline. |  | yes | s8 | high | low
money |  | Move savings to the higher-interest account | task |  |  |  | stuck |  | me |  |  | The bank app keeps rejecting the ID photo. Try at the branch. |  | yes | s9 | high | low
money |  | Sort the paper folder of old bills | task |  |  |  | todo |  | me |  |  |  |  | yes | s10 | low | low
health |  | Pedicure | task |  |  | 2026-10-16 | todo |  | me |  |  | Friday afternoons at the salon on Via Roma |  | yes | s11 | high | low | every 2 weeks
health |  | Yearly blood test | task |  |  | 2026-10-20 | waiting |  | Dr. Weiss |  |  | Waiting for the referral from the GP |  | yes | s12 | high | low
health |  | Swim at the pool | task |  |  | 2026-10-13 | doing |  | me |  |  | Tuesday mornings |  | yes | s13 | high | low | weekly

## Settings
key | value | meaning
lite | 1 | Version of the life-crm lite format. Leave it at 1.
title | Elena's plan | Title shown at the top of the page
name | Elena | Your name
updated | 2026-10-11 | Date of the last change (YYYY-MM-DD)
tone | caring | How the assistant talks to you: kick, caring, motivational or none
tone_line | You don't have to do it all this week. Pick the paint colour today and let the rest wait. | One line in that tone, shown at the top of the page (empty for none)
sheet_url | https://docs.google.com/spreadsheets/d/EXAMPLE-elena | Link to this sheet
account | elena.rossi@example.com | Google account this sheet is saved in

## Collections
id | name | tab | layout | title_field | status_field | statuses | date_field | fields | group | icon | description | empty_text | show | order | area
subscriptions | Subscriptions | Subscriptions | table | subscription |  |  | renews | cost, renews, decision | Money |  |  |  | yes | 1 | money
people | People | People | table | name |  |  |  | role, area, contact | People |  |  |  | yes | 2

## People
name | role | area | contact
Marco | Painter, living room | home
Giulia | Friend visiting 6–10 November | home
Luca | Neighbour, can help carry boxes | home
Avv. Bianchi | Lawyer, has the will ready to sign | money
Dr. Weiss | GP, referral for the blood test | health

## Subscriptions
subscription | cost | renews | decision
Gym membership | €39 / month | 2026-11-01 | cancel
Streaming service A | €13 / month | 2026-10-19 | keep
Streaming service B | €9 / month | 2026-10-27 | cancel
Cloud storage | €2 / month | 2026-10-30 | keep
Cooking magazine | €48 / year | 2027-01-15 | check
Language app | €80 / year | 2026-12-03 | check